## Timeline
| Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
When? | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28 | 2015-11-29 | 2015-11-30 | 2015-12-01 | 2015-12-02 | 2015-12-03 | 2015-12-04 | 2015-12-05 | 2015-12-06 | 2015-12-07 | 2015-12-08 | 2015-12-09 | 2015-12-10
What? | 2015-12-10: Deadline for Website, Video(Screencast), Ipython Notebook
Line | 2015-11-23: download & convert data; 2015-12-07: Presentation Slides; 2015-12-09: Website
| create first model for delay time | [14 empty] | Video
create first model for best airline

## Tasklist
Tasklist
| David |  |  | Estienne |  |  | Leonhard |  |  | Victor
| What? | Status | Due? | What? | Status | Due? | What? | Status | Due? | What? | Status | Due?
| research based on data what plane serves a flight (plane model & age) | Done. Script and Information finished, has just to be applied to the full dataset as soon as we decided which one to use | Tue, 24.11 | get a dataset which party rules which state (US) |  | Tue, 24.11 | http://www.transtats.bts.gov/DL_SelectFields.asp?Table_ID=236&DB_Short_Name=On-Time write a script that gets the data from the website | Done | Tue, 24.11 Done | Rankings (in terms of delay time) 10 top airlines / 10 worst airlines 10 top airports / 10 worst airports 10 top combination / 10 worst combination | Done | Th, 26.11
| sample small dataset out of original data | Done. "Small" is still pretty big (ca. 2GB), can adjust it if necessary. Please use script as outlined on Slack. | Wed, 25.11 | think of way to deal with airlines that merged (i.e. United/Continental) |  | Th, 26.11 | download data for key mappings | Done | Tue, 01.12. | restrict dataset to active airlines only | Done | Th, 26.11
| get information which airlines merged the last years | Done. For sample data from 2014 no mergers are relevant. All other can be found at https://en.wikipedia.org/wiki/List_of_airline_mergers_and_acquisitions | Wed, 25.11 | think of mathematical model, in order to predict (a) what is the best airline (b) delay time for given input data | Done | Fr, 28.11. | write work done into Process notebook | Done | Wed, 02.12. | write work done into Process notebook |  | Wed, 02.12.
| Apply all preprocessing tasks (e.g. plane age, data reduction, if applicable also mergers) to dataset | Done. No relevant mergers found. Everything else integrated in the data reduction/preparation script. | Thu, 26.11 | Plot average times AirFrance/KLM and for Continental/United graphs and check if there are any changes in behaviour |  | Wed, 02.12.2012 | fix the download file script --> it is all january there is some error | Done | Wed, 02.12. | looking at the breakdown of delays (security delays / weather delays / …) |  | Wed, 02.12.
| Do research on external weather data | Done | Thu, 26.11 | write work done into Process notebook |  | Wed, 02.12. | support Estienne on model |  | Fr, 04.12 | combination for routes (i.e. which route has best/worst delay times --> do a top10/flop10 ranking) |  | Th, 03.12
| write work done into Process notebook | Done | Wed, 02.12. | fit a Random forest model, neural network, linear regression to data (sparse it out if necessary --> focus only on major airlines) |  | Fr, 04.12. | create map ("heatmap") visualization of airports & delay times |  | Sa, 06.12. | evolution of airline average delay time over time (for 20 most popular airlines) --> nice visualization |  | Fr, 04.12.
| add ipython chapter dummy files with outline structure | Done | Thu, 03.12. |  |  |  | delay time per dollar for current flight (pick some route ie. New York <-> Chicago |  | Fr, 05.12. | beautify plots with seaborn / real airline names so that they are deliverable |  | So, 05.12.
| get weather data (snow height, amount of rain, type, …) | Done (Leonhard) | Th, 03.12. |  |  |  | build downloadscript for weather data | Done | Fr, 05.12. | work on Website / establish template |  | Mo, 07.12.
| analysis of correlation / dependence between weather and data | Done for JFK | Fr, 04.12.
| layout first slides for video | Done | Tue, 08.12.
| Finish first video draft |  | Tue, 08.12.